## Timeline and Checklist
Event Name
Date
Venue
Planning Timeline
Task | Lead Volunteer | Deadline | Complete | Notes
6-12 Months Before Event
Brainstorm event ideas and determine fundraising goal
Establish the date of the event and visit possible event locations
Form a planning committee
Develop a list of prospective participants (family, friends, community members, etc.) to invite. Compile and organize email/mailing list.
Identify additional participants and outreach plan. Create sponsorship list.
Research and obtain cost estimates for venue, food and beverages, entertainment, etc.
Create an initial budget including music, décor, printing, photography, etc. Determine what can be donated and what will have to be paid for personally.
Complete and send the Community Fundraising Event Application to Meghan McMurray for approval before further planning
Begin working on the invitation/flyer/email design
Three to Six Months Before Event
Conduct committee meetings to confirm the event is on track
Send requests for sponsorships, if needed
Prepare final copy for all printed materials and send to Meghan McMurray for approval before distribution
Sign contracts with all vendors (including insurance and permits, if needed)
Select menu if food will be served
Confirm speakers and entertainment
Two Months Before Event
Send invitations and/or evites
Follow up to confirm sponsorships
Follow up with participants about fundraising and encouraging them to attend
Create marketing materials (banners, tickets, posters, etc.) for the event if needed
One Month Before Event
Finalize day-of timeline
Confirm volunteers, entertainment, food/beverage
Final push for donations and sponsorships
Finalize the event day itinerary
Purchase décor needed for the event
One Week Before Event
Confirm final number of guests attending
Create a packing list for event materials
Hold final meeting with committee and event volunteers
Double-check delivery times and drop-off locations with all vendors
Day of Event
Arrive early to unpack and set up materials to ensure all items are accounted for
Set up registration area
Check in with volunteers and conduct a run-through
Check in with vendors
Enjoy the event!
After Event (within 14 days)
Submit photos and an event recap to UCSF BCHs
Post recap on your social media accounts
Count all money collected on the day of the event
Send all checks made payable to “UCSF Benioff Children's Hospitals” to 2201 Broadway Suite 600 Oakland, CA 94612
Send thank-you notes to donors and sponsors